## overAllChart
Basic Skeleton | Pages | Registration forms | Started Date | Ended Date | Commands | Images | pending | completed | yet to complete | ReportBySaravnan
UI Design | Login Page | Client
| Register Page | customer | 2019-02-02 | 2019-07-02 | I have completed and I have added in github |  | No | Yes | No
| Forget Password | management
| Introduction Page | catalogs
| Home Page | employees
Packages
Controller
Middle Layer | Request |  | 2019-12-02 | Today Working |  |  | Yes Need to Update | Working | Yes
| DAO |  |  | 2019-01-03
Bean
Connection
Utility
Back End | Database Design |  | 2019-08-02 | 2019-11-02 | I have completed and I have notes and images |  | No | Yes | No
| DataFlow |  |  |  | and I have submitted too
Tables
| Columns |  |  |  | tables and columns are created and updated in github

## classes
Controller | DAO | Request | Bean | Connection | utility
Inventory Controller | InventoryDAO | Inventory Request | InventoryDetails | InventoryConnection | InventoryUtility
InventoryLogin
InventoryRegister
InventoryClient
InventoryNormalClient
inventoryCompanyClient
InventoryCustomer
InventoryNormalCustomer
InventoryCompanyCustomer
InventoryEmployee
InventorySalesTeam
InventoryProcurementTeam
InventoryFinanceTeam
InventoryTechnicianTeam
InventoryManagement
InventoryDirector
InventoryManagingDirector
InventoryGeneralManager
InventoryManager
InventoryCatalog
InventoryLaptop
InventoryDesktop
InventoryTablet
InventoryServer
InventoryReport
InventoryTechnicianReportOnCatalog
InventoryClientReport
InventoryCustomerReport
InventoryReportOnTechnicianByManagement
InventoryNeedToBeService
InventoryScrap
InventorySpair
InventoryReadyForSale

## methods
|  | METHODS FOR ALL CLASSES |  | InventoryBean
InventoryControllerMethods | InventoryDAOMethods | inventoryRequest | InventoryConnections
InventoryLoginDetails | InventoryLoginDetails |  | InventoryLoginDetails
InventoryRegisterDetails | InventoryRegisterDetails |  | InventoryRegisterDetails
InventoryClient | InventoryClient |  | InventoryClient
InventoryNormalClient | InventoryNormalClient |  | InventoryNormalClient
inventoryCompanyClient | inventoryCompanyClient |  | inventoryCompanyClient
InventoryCustomer | InventoryCustomer |  | InventoryCustomer
InventoryNormalCustomer | InventoryNormalCustomer |  | InventoryNormalCustomer
InventoryCompanyCustomer | InventoryCompanyCustomer |  | InventoryCompanyCustomer
InventoryEmployee | InventoryEmployee |  | InventoryEmployee
InventorySalesTeam | InventorySalesTeam |  | InventorySalesTeam
InventoryProcurementTeam | InventoryProcurementTeam |  | InventoryProcurementTeam
InventoryFinanceTeam | InventoryFinanceTeam |  | InventoryFinanceTeam
InventoryTechnicianTeam | InventoryTechnicianTeam |  | InventoryTechnicianTeam
InventoryManagement | InventoryManagement |  | InventoryManagement
InventoryDirector | InventoryDirector |  | InventoryDirector
InventoryManagingDirector | InventoryManagingDirector |  | InventoryManagingDirector
InventoryGeneralManager | InventoryGeneralManager |  | InventoryGeneralManager
InventoryManager | InventoryManager |  | InventoryManager
InventoryCatalog | InventoryCatalog |  | InventoryCatalog
InventoryAddByLaptop | InventoryAddByLaptop |  | InventoryAddByLaptop
InventoryAddByDesktop | InventoryAddByDesktop |  | InventoryAddByDesktop
InventoryAddByTablet | InventoryAddByTablet |  | InventoryAddByTablet
InventoryAddByServer | InventoryAddByServer |  | InventoryAddByServer
InventoryReport | InventoryReport |  | InventoryReport
InventoryTechnicianReportOnCatalog | InventoryTechnicianReportOnCatalog |  | InventoryTechnicianReportOnCatalog
InventoryClientReport | InventoryClientReport |  | InventoryClientReport
InventoryCustomerReport | InventoryCustomerReport |  | InventoryCustomerReport
InventoryReportOnTechnicianByManagement | InventoryReportOnTechnicianByManagement |  | InventoryReportOnTechnicianByManagement
InventoryNeedToBeService | InventoryNeedToBeService |  | InventoryNeedToBeService
InventoryScrap | InventoryScrap |  | InventoryScrap
InventorySpair | InventorySpair |  | InventorySpair
InventoryReadyForSale | InventoryReadyForSale |  | InventoryReadyForSale